## Headings
Heading Number | Heading Name | Page No | Font Size | Style
1 | Purpose | 2 | 10 | Normal
2 | Scope | 2 | 10 | Normal
3 | Roles and responsibilities | 2 | 10 | Normal
4 | Contact information and communications. | 2 | 10 | Normal
5 | IT recovery planning | 2 | 10 | Normal
5.1 | IT recovery strategy | 2 | 10 | Normal
5.2 | IT recovery priorities | 2 | 10 | Normal
5.3 | Backup and restore information | 2 | 10 | Normal
5.4 | IT recovery list | 2 | 10 | Normal
5.5 | Release of IT solution after recovery (Post-recovery check) | 2 | 10 | Normal
6 | Testing of the IT recovery plan | 2 | 10 | Normal
6.1.1 | Recovery testing | 2 | 10 | Normal
6.1.1.1.1 | Reporting the result | 2 | 10 | Normal
7 | References | 2 | 10 | Normal
8 | Change log | 2 | 10 | Normal
| Enclosure 1 – Test Documentation | 8 | 12 | Heading 1

## Bullets
Bullet Point | Bullet Point Text | Level | Page No
1. | Purpose | 2 | 3
2. | Scope | 2 | 3
● | IT Systems [1] | 2 | 3
● | IT Security [2] | 2 | 3
● | Data integrity [3] | 2 | 3
● | Infrastructure [4] | 2 | 3
● | Ownership of systems [5] | 2 | 3
o | Service description according to Infrastructure [4] | 2 | 3
o | Server1.test.local | 2 | 3
| Server2.test.local | 3 | 3
| Server3.test.local | 4 | 3
3. | Roles and responsibilities | 2 | 3
4. | Contact information and communications. | 2 | 4
5. | IT recovery planning | 2 | 4
5.1. | IT recovery strategy | 3 | 4
5.2. | IT recovery priorities | 3 | 4
5.3. | Backup and restore information | 3 | 4
5.4. | IT recovery list | 3 | 4
5.5. | Release of IT solution after recovery (Post-recovery check) | 3 | 5
1. | Log-on to the IT system | 2 | 5
2. | <Next steps> | 2 | 5
6. | Testing of the IT recovery plan | 2 | 5
6.1.1. | Recovery testing | 4 | 5
1. | RTO/RPO as defined is observed | 2 | 5
2. | Check that services are running | 2 | 5
6.1.1.1.1. | Reporting the result | 6 | 5
7. | References | 2 | 5
8. | Change log | 2 | 6
1. | RTO and RPO as defined in the service are observed in the test results. | 2 | 8
2. | Log-on to the server is possible. | 2 | 8
3. | Check that services are running. | 2 | 8

## Content Chunks
Content | Page No | Chunk | Font Size
This document is signed electronically using QualityDocs. | 1 | Paragraph on page 1 | 10
Signatures appear on a separate signature page. | 1 | Paragraph on page 1 | 10
Business Management and Operations | 1 | Paragraph on page 1 | 10
Appendix 1: IT recovery test report 8 | 2 | Paragraph on page 2 | 10
Enclosure 1 – Test Documentation 9 | 2 | Paragraph on page 2 | 10
The purpose of this IT recovery plan for ‘Backup’ service is to describe IT recovery to ensure recovery from a major incident or disaster as quickly as possible and with minimal disruption. | 3 | Paragraph on page 3 | 9
The IT recovery plan is based on the requirements in the Guideline]. | 3 | Paragraph on page 3 | 10
Go to the Quality Portal to see definitions of terms used in this document. More information is on Roles and responsibilities. | 3 | Paragraph on page 3 | 10
The activities outlined in this document will be executed and reported on according to the following NN instructions: | 3 | Paragraph on page 3 | 10
The IT recovery plan for Backup service reflects the IT recovery framework shown in Figure 1 (figure from google) and covers: | 3 | Paragraph on page 3 | 10
Each management instance, with servers in scope for this Recovery Plan are: | 3 | Paragraph on page 3 | 10
Figure 1 - IT recovery framework (picture from google) | 3 | Paragraph on page 3 | 8
Roles and responsibilities | 3 | Paragraph on page 3 | 12
For roles and responsibilities of Recovery Plan for the IT Service see ‘Disaster Recovery’ [6]. | 3 | Paragraph on page 3 | 10
Contact information and communications. | 4 | Paragraph on page 4 | 12
The contact information and actions that must be in place. | 4 | Paragraph on page 4 | 10
How<mobile no/ mail/other> | 4 | Paragraph on page 4 | 8
Go to the Quality Portal to see other descriptions of responsibilities for roles used in this guideline. | 4 | Paragraph on page 4 | 10
IT recovery planning | 4 | Paragraph on page 4 | 12
IT recovery strategy | 4 | Paragraph on page 4 | 12
The recovery approach is concentrated on bringing the server back online. | 4 | Paragraph on page 4 | 10
Dependencies: Following are the dependencies to recover Backup service. | 4 | Paragraph on page 4 | 10
IT recovery priorities | 4 | Paragraph on page 4 | 12
The following components have been identified to be critical to the operation of Backup services and data integrity: | 4 | Paragraph on page 4 | 10
Restore virtual server | 4 | Paragraph on page 4 | 10
RTO and RPO for each component are listed in the table below. | 4 | Paragraph on page 4 | 10
Backup and restore information | 4 | Paragraph on page 4 | 12
This information is found in ref. Backup operations [7]. | 4 | Paragraph on page 4 | 10
IT recovery list | 4 | Paragraph on page 4 | 12
The listed documents must be available in case of a major incident or disaster. | 4 | Paragraph on page 4 | 10
Recovery Plan (this plan) | 4 | Paragraph on page 4 | 10
Contact information (if not documented in this plan) | 5 | Paragraph on page 5 | 10
See section 4 | 5 | Paragraph on page 5 | 10
QualityDocs ID: Q200001, Backup operations | 5 | Paragraph on page 5 | 10
Refer SNow ITOM 1009 | 5 | Paragraph on page 5 | 10
Relevant SOPs or guidance | 5 | Paragraph on page 5 | 10
QualityDocs ID: Q200002, Infrastructure Operations and Maintenance | 5 | Paragraph on page 5 | 10
QD ID: Q200001, Backup operations | 5 | Paragraph on page 5 | 10
Release of IT solution after recovery (Post-recovery check) | 5 | Paragraph on page 5 | 12
To release the recovered Backup service to the users, the Service Manager performs the activities: | 5 | Paragraph on page 5 | 10
Log-on to the IT system | 5 | Paragraph on page 5 | 10
Testing of the IT recovery plan | 5 | Paragraph on page 5 | 12
Recovery testing is done in case of in case of any major changes as per Infrastructure Operations and Maintenance. | 5 | Paragraph on page 5 | 10
Test Strategy/ description | 5 | Paragraph on page 5 | 10
Restore the snapshot backup and test | 5 | Paragraph on page 5 | 10
RTO/RPO as defined is observed | 5 | Paragraph on page 5 | 10
Check that services are running | 5 | Paragraph on page 5 | 10
Once in x years | 5 | Paragraph on page 5 | 10
The RTO and RPO for the service in scope were defined in section 5.2. Contact information and content of the document are reviewed periodically. | 5 | Paragraph on page 5 | 10
Reporting the result | 5 | Paragraph on page 5 | 12
Conclusion on the review, including any follow-up actions are documented in Appendix 2. Also, the RTO and RPO for the recovery test performed were observed to be within the recovery times. | 5 | Paragraph on page 5 | 10
Q100001 IT Systems. | 5 | Paragraph on page 5 | 10
Q100002 IT Security. | 5 | Paragraph on page 5 | 10
Q100003 Data integrity. | 5 | Paragraph on page 5 | 10
Q100007 Ownership of Systems. | 5 | Paragraph on page 5 | 10
Q100005 Disaster Recovery. | 5 | Paragraph on page 5 | 10
Q100006 Backup operations. | 5 | Paragraph on page 5 | 10
Recovery plan for new service | 6 | Paragraph on page 6 | 10
Performed recovery test for this service. | 6 | Paragraph on page 6 | 10
Appendix 1: IT recovery test report | 7 | Paragraph on page 7 | 12
Review of contact information | 7 | Paragraph on page 7 | 10
Contact information reviewed and updated | 7 | Paragraph on page 7 | 10
This document. Section 4. | 7 | Paragraph on page 7 | 10
Recovery file reviewed and updated | 7 | Paragraph on page 7 | 10
This document, Enclosure 1 | 7 | Paragraph on page 7 | 10
Solution recovery testing | 7 | Paragraph on page 7 | 10
Doc. reference or summary | 7 | Paragraph on page 7 | 10
Test of solution recovery according to description in section ‎7. | 7 | Paragraph on page 7 | 10
Enclosure 1 – Test Documentation | 7 | Paragraph on page 7 | 10
Annual recovery is done as part of the incident INC0001, and service is recovered successfully. Also, RTO and RPO was observed to be within limits as mentioned in the BA. | 7 | Paragraph on page 7 | 10
RTO and RPO as defined in the service are observed in the test results. | 8 | Paragraph on page 8 | 10
RPO: The RPO is observed to be xx hours. | 8 | Paragraph on page 8 | 10
RTO: RTO is observed to be yy hours | 8 | Paragraph on page 8 | 10
<image 2.jpg > | 8 | Paragraph on page 8 | 10
Log-on to the server is possible. | 8 | Paragraph on page 8 | 10
<image 3.jpg > | 8 | Paragraph on page 8 | 10
Check that services are running. | 8 | Paragraph on page 8 | 10
<image 4.jpg > | 8 | Paragraph on page 8 | 10